## tickets extract
Name | Tag | Start Date | End Date | Priority
Communication Setup in Microsoft Teams | Development | December 9, 2024 | December 9, 2024 | High Priority
GitHub Repository Configuration | Development | December 10, 2024 | December 10, 2024 | High Priority
CI/CD Integration in GitHub | Development | December 11, 2024 | December 11, 2024 | High Priority
AWS Organizations Configuration for Cloud Management | Development | December 12, 2024 | December 12, 2024 | High Priority
VS Code Environment Configuration | Development | January 26, 2025 | January 26, 2025 | Medium Priority
Scrum and Sprint-Based Project Management Setup | Development | December 13, 2024 | December 13, 2024 | High Priority
Sprint Planning and Task Allocation | Development | December 14, 2024 | December 14, 2024 | High Priority
Sprint Retrospective Setup and Process | Development | January 27, 2025 | January 27, 2025 | Medium Priority
Development Workflow Documentation | Development | January 28, 2025 | January 28, 2025 | Medium Priority
Terraform Configuration for AWS Resources | Infrastructure | December 24, 2024 | December 24, 2024 | High Priority
VPC and Subnet Configuration | Infrastructure | December 25, 2024 | December 25, 2024 | High Priority
ECS Cluster Setup for Container Orchestration | Infrastructure | December 26, 2024 | December 27, 2024 | High Priority
Dockerization of Microservices | Infrastructure | December 28, 2024 | December 29, 2024 | High Priority
API Gateway Setup with Kong | Infrastructure | December 30, 2024 | December 31, 2024 | High Priority
CI/CD Pipeline Setup with AWS CodeBuild and GitHub | Infrastructure | January 1, 2025 | January 2, 2025 | High Priority
DocumentDB Configuration and Integration | Infrastructure | January 3, 2025 | January 3, 2025 | High Priority
Separate Production and Development Environments | Infrastructure | January 4, 2025 | January 5, 2025 | High Priority
Load Balancer and Auto Scaling Setup | Infrastructure | January 29, 2025 | January 29, 2025 | Medium Priority
Monitoring and Logging with AWS CloudWatch | Infrastructure | January 30, 2025 | January 30, 2025 | Medium Priority
Security and Compliance Configuration | Infrastructure | January 6, 2025 | January 6, 2025 | High Priority
Backup and Disaster Recovery Setup | Infrastructure | January 31, 2025 | January 31, 2025 | Medium Priority
Infrastructure Documentation and Handover | Infrastructure | February 1, 2025 | February 1, 2025 | Medium Priority
AWS DocumentDB Cluster Setup | Database | January 7, 2025 | January 7, 2025 | High Priority
Database Security Configuration | Database | January 8, 2025 | January 8, 2025 | High Priority
Database Schema and Collection Design | Database | January 9, 2025 | January 10, 2025 | High Priority
Data Backup and Recovery Configuration | Database | January 11, 2025 | January 12, 2025 | High Priority
GraphQL API for Content Retrieval | Database | January 13, 2025 | January 14, 2025 | High Priority
Monitoring and Logging with CloudWatch | Database | December 10, 2024 | December 10, 2024 | Medium Priority
Database Performance Optimization | Database | December 11, 2024 | December 12, 2024 | Medium Priority
Data Protection and GDPR Compliance | Database | January 15, 2025 | January 15, 2025 | High Priority
Documentation and Knowledge Transfer | Database | December 13, 2024 | December 13, 2024 | Medium Priority
Monorepo Setup and Configuration | BackEnd | January 16, 2025 | January 16, 2025 | High Priority
Authentication Microservice - Basic Setup | BackEnd | January 17, 2025 | January 17, 2025 | High Priority
Authentication Microservice - Role-Based Access Control (RBAC) | BackEnd | January 18, 2025 | January 18, 2025 | High Priority
Authentication Microservice - Middleware and Security | BackEnd | January 19, 2025 | January 19, 2025 | High Priority
Database Microservice - Basic Setup | BackEnd | January 20, 2025 | January 21, 2025 | High Priority
Database Microservice - GraphQL API with Apollo Server | BackEnd | January 22, 2025 | January 23, 2025 | High Priority
Database Microservice - Data Validation and Error Handling | BackEnd | December 14, 2024 | December 14, 2024 | Medium Priority
CMS Microservice - Payload Integration Setup | BackEnd | January 24, 2025 | January 25, 2025 | High Priority
CMS Microservice - GraphQL API for Content Management | BackEnd | January 26, 2025 | January 27, 2025 | High Priority
Shared Authentication Across Microservices | BackEnd | January 28, 2025 | January 28, 2025 | High Priority
Performance Optimization for GraphQL Endpoints | BackEnd | December 15, 2024 | December 16, 2024 | Medium Priority
API Gateway Setup | BackEnd | January 29, 2025 | January 29, 2025 | High Priority
CI/CD Pipeline for Backend Deployment | BackEnd | January 30, 2025 | January 31, 2025 | High Priority
Documentation and Knowledge Transfer | BackEnd | December 17, 2024 | December 17, 2024 | Medium Priority
CMS Environment Setup | CMS | December 9, 2024 | December 9, 2024 | High Priority
Define Content Models and Fields | CMS | December 9, 2024 | December 9, 2024 | High Priority
Role-Based Access and Permissions | CMS | December 9, 2024 | December 9, 2024 | High Priority
Media Library Setup | CMS | December 18, 2024 | December 18, 2024 | Medium Priority
GraphQL API Setup | CMS | December 9, 2024 | December 9, 2024 | High Priority
Integration with Next.js using TypeScript | CMS | December 10, 2024 | December 12, 2024 | High Priority
Real-Time Preview Setup | CMS | December 19, 2024 | December 20, 2024 | Medium Priority
CMS Security and Authentication | CMS | December 12, 2024 | December 12, 2024 | High Priority
CMS Content Creation Training | CMS | December 21, 2024 | December 22, 2024 | Medium Priority
Deployment Configuration | CMS | December 13, 2024 | December 13, 2024 | High Priority
CMS Deployment to Production | CMS | December 14, 2024 | December 14, 2024 | High Priority
Ongoing Support and Maintenance | CMS | February 1, 2025 | February 1, 2025 | Medium Priority
Design Setup in Figma | Figma | December 15, 2024 | December 15, 2024 | High Priority
Branding Guideline Integration | Figma | December 16, 2024 | December 16, 2024 | High Priority
Atom Design Creation | Figma | December 23, 2024 | December 24, 2024 | Medium Priority
Molecule Design Creation | Figma | December 25, 2024 | December 26, 2024 | Medium Priority
Organism Design Creation | Figma | December 27, 2024 | December 29, 2024 | Medium Priority
Layout and Page Design | Figma | December 17, 2024 | December 19, 2024 | High Priority
Interactive Prototyping | Figma | December 30, 2024 | December 31, 2024 | Medium Priority
Documentation of Design Decisions | Figma | December 19, 2024 | December 20, 2024 | High Priority
Collaboration and Review Sessions | Figma | February 1, 2025 | February 1, 2025 | Medium Priority
Project Setup and Configuration | FrontEnd | December 21, 2024 | December 21, 2024 | High Priority
Responsive and Modern Homepage Design | FrontEnd | December 22, 2024 | December 24, 2024 | High Priority
Enhanced Search Functionality | FrontEnd | December 25, 2024 | December 27, 2024 | High Priority
Home Sales Pages | FrontEnd | December 27, 2024 | December 31, 2024 | High Priority
Contact Forms Implementation | FrontEnd | January 1, 2025 | January 2, 2025 | Medium Priority
Service Pages | FrontEnd | January 3, 2025 | January 5, 2025 | Medium Priority
News and Updates Section | FrontEnd | January 6, 2025 | January 7, 2025 | Medium Priority
Accessibility and WCAG 2.2 Compliance | FrontEnd | January 1, 2025 | January 3, 2025 | High Priority
SEO Optimization | FrontEnd | January 8, 2025 | January 9, 2025 | Medium Priority
CMS Integration | FrontEnd | January 4, 2025 | January 7, 2025 | High Priority
Browser Compatibility | FrontEnd | January 10, 2025 | January 10, 2025 | Medium Priority
Video and Image Capability | FrontEnd | January 11, 2025 | January 12, 2025 | Medium Priority
Analytics Integration | FrontEnd | January 13, 2025 | January 13, 2025 | Medium Priority
Backend API Integration | FrontEnd | January 8, 2025 | January 10, 2025 | High Priority
Authentication (Optional) | FrontEnd | January 14, 2025 | January 15, 2025 | Medium Priority
Training and Documentation | FrontEnd | February 1, 2025 | February 1, 2025 | Low Priority
Ongoing Support and Maintenance | FrontEnd | February 1, 2025 | February 1, 2025 | Low Priority
Set Up Dedicated Testing Environment | Testing | January 11, 2025 | January 11, 2025 | High Priority
Unit Testing Setup for Backend Microservices | Testing | January 12, 2025 | January 12, 2025 | High Priority
Unit Tests for Authentication Microservice | Testing | January 13, 2025 | January 14, 2025 | High Priority
Unit Tests for Database Microservice | Testing | January 15, 2025 | January 16, 2025 | High Priority
Unit Tests for CMS Microservice (Payload Integration) | Testing | January 16, 2025 | January 17, 2025 | Medium Priority
Unit Testing Setup for Frontend Components | Testing | January 16, 2025 | January 16, 2025 | High Priority
Unit Tests for Frontend UI Components (Atoms and Molecules) | Testing | January 18, 2025 | January 19, 2025 | Medium Priority
Unit Tests for Frontend Organisms and Pages | Testing | January 20, 2025 | January 22, 2025 | Medium Priority
Integration Testing Setup for Frontend (Cypress) | Testing | January 17, 2025 | January 17, 2025 | High Priority
Integration Tests for User Authentication Flows | Testing | January 18, 2025 | January 19, 2025 | High Priority
Integration Tests for Content Management and Display | Testing | January 20, 2025 | January 21, 2025 | High Priority
Integration Tests for Key User Flows (Forms, Search) | Testing | January 23, 2025 | January 25, 2025 | Medium Priority
Continuous Integration of Testing in CI/CD Pipeline | Testing | January 22, 2025 | January 22, 2025 | High Priority
Test Documentation and Coverage Report | Testing | January 26, 2025 | January 26, 2025 | Medium Priority
Technical Architecture Documentation | Maintenance & Documentation | January 23, 2025 | January 24, 2025 | High Priority
Content Management Guide for Non-Technical Staff | Maintenance & Documentation | January 25, 2025 | January 26, 2025 | High Priority
API Documentation for Frontend Integration | Maintenance & Documentation | January 27, 2025 | January 27, 2025 | Medium Priority
Developer Onboarding Guide | Maintenance & Documentation | January 28, 2025 | January 28, 2025 | Medium Priority
Scheduled Maintenance Plan | Maintenance & Documentation | January 27, 2025 | January 27, 2025 | High Priority
Backup and Disaster Recovery Configuration | Maintenance & Documentation | January 28, 2025 | January 28, 2025 | High Priority
Security Audit and Compliance Documentation | Maintenance & Documentation | January 29, 2025 | January 30, 2025 | High Priority
Initial Training Sessions for Non-Technical Staff | Maintenance & Documentation | January 31, 2025 | January 31, 2025 | High Priority
Create Video Tutorials and Quick Reference Guides | Maintenance & Documentation | January 29, 2025 | January 30, 2025 | Medium Priority
Follow-Up Training and Q&A Session | Maintenance & Documentation | January 31, 2025 | January 31, 2025 | Medium Priority
Ongoing Support Channel for CMS Assistance | Maintenance & Documentation | February 1, 2025 | February 1, 2025 | Medium Priority
Update and Review Maintenance Documentation | Maintenance & Documentation | February 1, 2025 | February 1, 2025 | Medium Priority

## raw
Name | Tag | Due Date | Assigned to | Status | Priority | Created time | Last edited time | Description | Sprint planning | Files
Communication Setup in Microsoft Teams | Development | December 9, 2024 | Khalil M | Not started | High Priority | November 12, 2024 6:58 PM | November 12, 2024 8:50 PM |  | Active Sprint
GitHub Repository Configuration | Development | December 10, 2024 | Khalil M | Not started | High Priority | November 12, 2024 6:59 PM | November 12, 2024 8:51 PM |  | Active Sprint
CI/CD Integration in GitHub | Development | December 11, 2024 | Khalil M | Not started | High Priority | November 12, 2024 7:00 PM | November 13, 2024 7:54 PM |  | Active Sprint
AWS Organizations Configuration for Cloud Management | Development | December 12, 2024 | Khalil M | Not started | High Priority | November 12, 2024 7:01 PM | November 12, 2024 8:51 PM |  | Active Sprint
VS Code Environment Configuration | Development | January 26, 2025 | Khalil M | Not started | Medium Priority | November 12, 2024 7:01 PM | November 13, 2024 7:42 PM |  | Active Sprint
Notion Workspace Setup for Documentation and Project Management | Development | November 12, 2024 | Aymane Cheikh | In progress | High Priority | November 12, 2024 7:02 PM | November 12, 2024 7:36 PM |  | Active Sprint
Scrum and Sprint-Based Project Management Setup | Development | December 13, 2024 | Khalil M | Not started | High Priority | November 12, 2024 7:03 PM | November 12, 2024 8:52 PM |  | Active Sprint
Sprint Planning and Task Allocation | Development | December 14, 2024 | Khalil M | Not started | High Priority | November 12, 2024 7:03 PM | November 12, 2024 8:52 PM |  | Active Sprint
Sprint Retrospective Setup and Process | Development | January 27, 2025 | Khalil M | Not started | Medium Priority | November 12, 2024 7:04 PM | November 13, 2024 7:42 PM |  | Active Sprint
Development Workflow Documentation | Development | January 28, 2025 | Khalil M | Not started | Medium Priority | November 12, 2024 7:05 PM | November 13, 2024 7:42 PM |  | Active Sprint
Terraform Configuration for AWS Resources | Infrastructure | December 24, 2024 | Khalil M | Not started | High Priority | November 12, 2024 6:11 PM | November 12, 2024 8:48 PM |  | Active Sprint
VPC and Subnet Configuration | Infrastructure | December 25, 2024 | Khalil M | Not started | High Priority | November 12, 2024 6:12 PM | November 12, 2024 8:48 PM |  | Active Sprint
ECS Cluster Setup for Container Orchestration | Infrastructure | December 26, 2024 → December 27, 2024 | Khalil M | Not started | High Priority | November 12, 2024 6:12 PM | November 12, 2024 8:48 PM |  | Active Sprint
Dockerization of Microservices | Infrastructure | December 28, 2024 → December 29, 2024 | Khalil M | Not started | High Priority | November 12, 2024 6:13 PM | November 12, 2024 8:47 PM |  | Active Sprint
API Gateway Setup with Kong | Infrastructure | December 30, 2024 → December 31, 2024 | Khalil M | Not started | High Priority | November 12, 2024 6:13 PM | November 12, 2024 8:47 PM |  | Active Sprint
CI/CD Pipeline Setup with AWS CodeBuild and GitHub | Infrastructure | January 1, 2025 → January 2, 2025 | Khalil M | Not started | High Priority | November 12, 2024 6:14 PM | November 12, 2024 8:47 PM |  | Active Sprint
DocumentDB Configuration and Integration | Infrastructure | January 3, 2025 | Khalil M | Not started | High Priority | November 12, 2024 6:15 PM | November 12, 2024 8:47 PM |  | Active Sprint
Separate Production and Development Environments | Infrastructure | January 4, 2025 → January 5, 2025 | Khalil M | Not started | High Priority | November 12, 2024 6:16 PM | November 12, 2024 8:46 PM |  | Active Sprint
Load Balancer and Auto Scaling Setup | Infrastructure | January 29, 2025 | Khalil M | Not started | Medium Priority | November 12, 2024 6:16 PM | November 13, 2024 7:41 PM |  | Active Sprint
Monitoring and Logging with AWS CloudWatch | Infrastructure | January 30, 2025 | Khalil M | Not started | Medium Priority | November 12, 2024 6:17 PM | November 13, 2024 7:41 PM |  | Active Sprint
Security and Compliance Configuration | Infrastructure | January 6, 2025 | Khalil M | Not started | High Priority | November 12, 2024 6:17 PM | November 12, 2024 8:46 PM |  | Active Sprint
Backup and Disaster Recovery Setup | Infrastructure | January 31, 2025 | Khalil M | Not started | Medium Priority | November 12, 2024 6:19 PM | November 13, 2024 7:41 PM |  | Active Sprint
Infrastructure Documentation and Handover | Infrastructure | February 1, 2025 | Khalil M | Not started | Medium Priority | November 12, 2024 6:20 PM | November 13, 2024 7:40 PM |  | Active Sprint
AWS DocumentDB Cluster Setup | Database | January 7, 2025 | Khalil M | Not started | High Priority | November 12, 2024 5:44 PM | November 12, 2024 8:46 PM |  | Active Sprint
Database Security Configuration | Database | January 8, 2025 | Khalil M | Not started | High Priority | November 12, 2024 5:46 PM | November 12, 2024 8:45 PM |  | Active Sprint
Database Schema and Collection Design | Database | January 9, 2025 → January 10, 2025 | Khalil M | Not started | High Priority | November 12, 2024 5:47 PM | November 12, 2024 8:45 PM |  | Active Sprint
Data Backup and Recovery Configuration | Database | January 11, 2025 → January 12, 2025 | Khalil M | Not started | High Priority | November 12, 2024 5:48 PM | November 12, 2024 8:45 PM |  | Active Sprint
GraphQL API for Content Retrieval | Database | January 13, 2025 → January 14, 2025 | Khalil M | Not started | High Priority | November 12, 2024 5:49 PM | November 12, 2024 8:45 PM |  | Active Sprint
Monitoring and Logging with CloudWatch | Database | December 10, 2024 | Khalil M | Not started | Medium Priority | November 12, 2024 5:49 PM | November 13, 2024 7:40 PM |  | Active Sprint
Database Performance Optimization | Database | December 11, 2024 → December 12, 2024 | Khalil M | Not started | Medium Priority | November 12, 2024 5:51 PM | November 13, 2024 7:40 PM |  | Active Sprint
Data Protection and GDPR Compliance | Database | January 15, 2025 | Khalil M | Not started | High Priority | November 12, 2024 5:51 PM | November 12, 2024 8:44 PM |  | Active Sprint
Documentation and Knowledge Transfer | Database | December 13, 2024 | Khalil M | Not started | Medium Priority | November 12, 2024 5:52 PM | November 13, 2024 7:40 PM |  | Active Sprint
Monorepo Setup and Configuration | BackEnd | January 16, 2025 | Khalil M | Not started | High Priority | November 12, 2024 5:54 PM | November 12, 2024 8:44 PM |  | Active Sprint
Authentication Microservice - Basic Setup | BackEnd | January 17, 2025 | Khalil M | Not started | High Priority | November 12, 2024 5:55 PM | November 12, 2024 8:44 PM |  | Active Sprint
Authentication Microservice - Role-Based Access Control (RBAC) | BackEnd | January 18, 2025 | Khalil M | Not started | High Priority | November 12, 2024 5:55 PM | November 12, 2024 8:44 PM |  | Active Sprint
Authentication Microservice - Middleware and Security | BackEnd | January 19, 2025 | Khalil M | Not started | High Priority | November 12, 2024 5:56 PM | November 12, 2024 8:43 PM |  | Active Sprint
Database Microservice - Basic Setup | BackEnd | January 20, 2025 → January 21, 2025 | Khalil M | Not started | High Priority | November 12, 2024 5:57 PM | November 12, 2024 8:43 PM |  | Active Sprint
Database Microservice - GraphQL API with Apollo Server | BackEnd | January 22, 2025 → January 23, 2025 | Khalil M | Not started | High Priority | November 12, 2024 5:58 PM | November 12, 2024 8:43 PM |  | Active Sprint
Database Microservice - Data Validation and Error Handling | BackEnd | December 14, 2024 | Khalil M | Not started | Medium Priority | November 12, 2024 5:59 PM | November 13, 2024 7:39 PM |  | Active Sprint
CMS Microservice - Payload Integration Setup | BackEnd | January 24, 2025 → January 25, 2025 | Khalil M | Not started | High Priority | November 12, 2024 6:00 PM | November 12, 2024 8:42 PM |  | Active Sprint
CMS Microservice - GraphQL API for Content Management | BackEnd | January 26, 2025 → January 27, 2025 | Khalil M | Not started | High Priority | November 12, 2024 6:01 PM | November 12, 2024 8:42 PM |  | Active Sprint
Shared Authentication Across Microservices | BackEnd | January 28, 2025 | Khalil M | Not started | High Priority | November 12, 2024 6:02 PM | November 12, 2024 8:42 PM |  | Active Sprint
Performance Optimization for GraphQL Endpoints | BackEnd | December 15, 2024 → December 16, 2024 | Khalil M | Not started | Medium Priority | November 12, 2024 6:04 PM | November 13, 2024 7:39 PM |  | Active Sprint
API Gateway Setup | BackEnd | January 29, 2025 | Khalil M | Not started | High Priority | November 12, 2024 6:05 PM | November 12, 2024 8:42 PM |  | Active Sprint
CI/CD Pipeline for Backend Deployment | BackEnd | January 30, 2025 → January 31, 2025 | Khalil M | Not started | High Priority | November 12, 2024 6:09 PM | November 12, 2024 8:41 PM |  | Active Sprint
Documentation and Knowledge Transfer | BackEnd | December 17, 2024 | Khalil M | Not started | Medium Priority | November 12, 2024 6:10 PM | November 13, 2024 7:39 PM |  | Active Sprint
CMS Environment Setup | CMS | December 9, 2024 | Khalil M | Not started | High Priority | November 11, 2024 10:33 PM | November 12, 2024 8:40 PM |  | Active Sprint
Define Content Models and Fields | CMS | December 9, 2024 | Khalil M | Not started | High Priority | November 11, 2024 10:34 PM | November 12, 2024 8:40 PM |  | Active Sprint
Role-Based Access and Permissions | CMS | December 9, 2024 | Khalil M | Not started | High Priority | November 11, 2024 10:35 PM | November 12, 2024 8:40 PM |  | Active Sprint
Media Library Setup | CMS | December 18, 2024 | Khalil M | Not started | Medium Priority | November 11, 2024 10:36 PM | November 13, 2024 7:39 PM |  | Active Sprint
GraphQL API Setup | CMS | December 9, 2024 | Khalil M | Not started | High Priority | November 11, 2024 10:37 PM | November 12, 2024 8:40 PM |  | Active Sprint
Integration with Next.js using TypeScript | CMS | December 10, 2024 → December 12, 2024 | Khalil M | Not started | High Priority | November 11, 2024 10:38 PM | November 12, 2024 8:39 PM |  | Active Sprint
Real-Time Preview Setup | CMS | December 19, 2024 → December 20, 2024 | Khalil M | Not started | Medium Priority | November 11, 2024 10:40 PM | November 13, 2024 7:38 PM |  | Active Sprint
CMS Security and Authentication | CMS | December 12, 2024 | Khalil M | Not started | High Priority | November 11, 2024 10:42 PM | November 12, 2024 8:38 PM |  | Active Sprint
CMS Content Creation Training | CMS | December 21, 2024 → December 22, 2024 | Khalil M | Not started | Medium Priority | November 11, 2024 10:43 PM | November 13, 2024 7:38 PM |  | Active Sprint
Deployment Configuration | CMS | December 13, 2024 | Khalil M | Not started | High Priority | November 11, 2024 10:44 PM | November 12, 2024 8:38 PM |  | Active Sprint
CMS Deployment to Production | CMS | December 14, 2024 | Khalil M | Not started | High Priority | November 11, 2024 10:45 PM | November 12, 2024 8:38 PM |  | Active Sprint
Ongoing Support and Maintenance | CMS | February 1, 2025 | Khalil M | Not started | Medium Priority | November 11, 2024 10:46 PM | November 13, 2024 7:43 PM |  | Active Sprint
Design Setup in Figma | Figma | December 15, 2024 | Khalil M | Not started | High Priority | November 11, 2024 10:48 PM | November 12, 2024 8:38 PM |  | Active Sprint
Branding Guideline Integration | Figma | December 16, 2024 | Khalil M | Not started | High Priority | November 11, 2024 10:49 PM | November 12, 2024 8:37 PM |  | Active Sprint
Atom Design Creation | Figma | December 23, 2024 → December 24, 2024 | Khalil M | Not started | Medium Priority | November 11, 2024 10:50 PM | November 13, 2024 7:37 PM |  | Active Sprint
Molecule Design Creation | Figma | December 25, 2024 → December 26, 2024 | Khalil M | Not started | Medium Priority | November 11, 2024 10:51 PM | November 13, 2024 7:37 PM |  | Active Sprint
Organism Design Creation | Figma | December 27, 2024 → December 29, 2024 | Khalil M | Not started | Medium Priority | November 11, 2024 10:53 PM | November 13, 2024 7:37 PM |  | Active Sprint
Layout and Page Design | Figma | December 17, 2024 → December 19, 2024 | Khalil M | Not started | High Priority | November 11, 2024 10:54 PM | November 12, 2024 8:37 PM |  | Active Sprint
Interactive Prototyping | Figma | December 30, 2024 → December 31, 2024 | Khalil M | Not started | Medium Priority | November 11, 2024 10:55 PM | November 13, 2024 7:37 PM |  | Active Sprint
Documentation of Design Decisions | Figma | December 19, 2024 → December 20, 2024 | Khalil M | Not started | High Priority | November 11, 2024 10:56 PM | November 12, 2024 8:35 PM |  | Active Sprint
Collaboration and Review Sessions | Figma | February 1, 2025 | Khalil M | Not started | Medium Priority | November 11, 2024 10:56 PM | November 13, 2024 7:43 PM |  | Active Sprint
Project Setup and Configuration | FrontEnd | December 21, 2024 | Khalil M | Not started | High Priority | November 11, 2024 10:05 PM | November 12, 2024 8:34 PM |  | Active Sprint
Responsive and Modern Homepage Design | FrontEnd | December 22, 2024 → December 24, 2024 | Khalil M | Not started | High Priority | November 11, 2024 10:09 PM | November 12, 2024 8:33 PM |  | Active Sprint
Enhanced Search Functionality | FrontEnd | December 25, 2024 → December 27, 2024 | Khalil M | Not started | High Priority | November 11, 2024 10:11 PM | November 12, 2024 8:33 PM |  | Active Sprint
Home Sales Pages | FrontEnd | December 27, 2024 → December 31, 2024 | Khalil M | Not started | High Priority | November 11, 2024 10:14 PM | November 12, 2024 8:32 PM |  | Active Sprint
Contact Forms Implementation | FrontEnd | January 1, 2025 → January 2, 2025 | Khalil M | Not started | Medium Priority | November 11, 2024 10:15 PM | November 13, 2024 7:31 PM |  | Active Sprint
Service Pages | FrontEnd | January 3, 2025 → January 5, 2025 | Khalil M | Not started | Medium Priority | November 11, 2024 10:17 PM | November 13, 2024 7:31 PM |  | Active Sprint
News and Updates Section | FrontEnd | January 6, 2025 → January 7, 2025 | Khalil M | Not started | Medium Priority | November 11, 2024 10:17 PM | November 13, 2024 7:31 PM |  | Active Sprint
Accessibility and WCAG 2.2 Compliance | FrontEnd | January 1, 2025 → January 3, 2025 | Khalil M | Not started | High Priority | November 11, 2024 10:18 PM | November 12, 2024 8:26 PM |  | Active Sprint
SEO Optimization | FrontEnd | January 8, 2025 → January 9, 2025 | Khalil M | Not started | Medium Priority | November 11, 2024 10:20 PM | November 13, 2024 7:31 PM |  | Active Sprint
CMS Integration | FrontEnd | January 4, 2025 → January 7, 2025 | Khalil M | Not started | High Priority | November 11, 2024 10:21 PM | November 12, 2024 8:31 PM |  | Active Sprint
Browser Compatibility | FrontEnd | January 10, 2025 | Khalil M | Not started | Medium Priority | November 11, 2024 10:22 PM | November 13, 2024 7:54 PM |  | Active Sprint
Video and Image Capability | FrontEnd | January 11, 2025 → January 12, 2025 | Khalil M | Not started | Medium Priority | November 11, 2024 10:25 PM | November 13, 2024 7:30 PM |  | Active Sprint
Analytics Integration | FrontEnd | January 13, 2025 | Khalil M | Not started | Medium Priority | November 11, 2024 10:26 PM | November 13, 2024 7:30 PM |  | Active Sprint
Backend API Integration | FrontEnd | January 8, 2025 → January 10, 2025 | Khalil M | Not started | High Priority | November 11, 2024 10:27 PM | November 12, 2024 8:31 PM |  | Active Sprint
Authentication (Optional) | FrontEnd | January 14, 2025 → January 15, 2025 | Khalil M | Not started | Medium Priority | November 11, 2024 10:28 PM | November 13, 2024 7:29 PM |  | Active Sprint
Training and Documentation | FrontEnd | February 1, 2025 | Khalil M | Not started | Low Priority | November 11, 2024 10:29 PM | November 13, 2024 7:42 PM |  | Active Sprint
Ongoing Support and Maintenance | FrontEnd | February 1, 2025 | Khalil M | Not started | Low Priority | November 11, 2024 10:30 PM | November 13, 2024 7:43 PM |  | Active Sprint
Set Up Dedicated Testing Environment | Testing | January 11, 2025 → January 11, 2025 | Khalil M | Not started | High Priority | November 12, 2024 6:45 PM | November 12, 2024 8:31 PM |  | Active Sprint
Unit Testing Setup for Backend Microservices | Testing | January 12, 2025 → January 12, 2025 | Khalil M | Not started | High Priority | November 12, 2024 6:46 PM | November 12, 2024 8:30 PM |  | Active Sprint
Unit Tests for Authentication Microservice | Testing | January 13, 2025 → January 14, 2025 | Khalil M | Not started | High Priority | November 12, 2024 6:47 PM | November 12, 2024 8:30 PM |  | Active Sprint
Unit Tests for Database Microservice | Testing | January 15, 2025 → January 16, 2025 | Khalil M | Not started | High Priority | November 12, 2024 6:47 PM | November 12, 2024 8:30 PM |  | Active Sprint
Unit Tests for CMS Microservice (Payload Integration) | Testing | January 16, 2025 → January 17, 2025 | Khalil M | Not started | Medium Priority | November 12, 2024 6:48 PM | November 13, 2024 7:28 PM |  | Active Sprint
Unit Testing Setup for Frontend Components | Testing | January 16, 2025 → January 16, 2025 | Khalil M | Not started | High Priority | November 12, 2024 6:49 PM | November 12, 2024 8:30 PM |  | Active Sprint
Unit Tests for Frontend UI Components (Atoms and Molecules) | Testing | January 18, 2025 → January 19, 2025 | Khalil M | Not started | Medium Priority | November 12, 2024 6:49 PM | November 13, 2024 7:28 PM |  | Active Sprint
Unit Tests for Frontend Organisms and Pages | Testing | January 20, 2025 → January 22, 2025 | Khalil M | Not started | Medium Priority | November 12, 2024 6:50 PM | November 13, 2024 7:27 PM |  | Active Sprint
Integration Testing Setup for Frontend (Cypress) | Testing | January 17, 2025 → January 17, 2025 | Khalil M | Not started | High Priority | November 12, 2024 6:51 PM | November 12, 2024 8:29 PM |  | Active Sprint
Integration Tests for User Authentication Flows | Testing | January 18, 2025 → January 19, 2025 | Khalil M | Not started | High Priority | November 12, 2024 6:52 PM | November 12, 2024 8:29 PM |  | Active Sprint
Integration Tests for Content Management and Display | Testing | January 20, 2025 → January 21, 2025 | Khalil M | Not started | High Priority | November 12, 2024 6:53 PM | November 12, 2024 8:29 PM |  | Active Sprint
Integration Tests for Key User Flows (Forms, Search) | Testing | January 23, 2025 → January 25, 2025 | Khalil M | Not started | Medium Priority | November 12, 2024 6:53 PM | November 13, 2024 7:27 PM |  | Active Sprint
Continuous Integration of Testing in CI/CD Pipeline | Testing | January 22, 2025 → January 22, 2025 | Khalil M | Not started | High Priority | November 12, 2024 6:54 PM | November 12, 2024 8:28 PM |  | Active Sprint
Test Documentation and Coverage Report | Testing | January 26, 2025 | Khalil M | Not started | Medium Priority | November 12, 2024 6:55 PM | November 13, 2024 7:26 PM |  | Active Sprint
Technical Architecture Documentation | Maintenance & Documentation | January 23, 2025 → January 24, 2025 | Khalil M | Not started | High Priority | November 12, 2024 7:06 PM | November 12, 2024 8:28 PM |  | Active Sprint
Content Management Guide for Non-Technical Staff | Maintenance & Documentation | January 25, 2025 → January 26, 2025 | Khalil M | Not started | High Priority | November 12, 2024 7:09 PM | November 12, 2024 8:28 PM |  | Active Sprint
API Documentation for Frontend Integration | Maintenance & Documentation | January 27, 2025 | Khalil M | Not started | Medium Priority | November 12, 2024 7:09 PM | November 13, 2024 7:26 PM |  | Active Sprint
Developer Onboarding Guide | Maintenance & Documentation | January 28, 2025 | Khalil M | Not started | Medium Priority | November 12, 2024 7:10 PM | November 13, 2024 7:26 PM |  | Active Sprint
Scheduled Maintenance Plan | Maintenance & Documentation | January 27, 2025 → January 27, 2025 | Khalil M | Not started | High Priority | November 12, 2024 7:11 PM | November 12, 2024 8:27 PM |  | Active Sprint
Backup and Disaster Recovery Configuration | Maintenance & Documentation | January 28, 2025 → January 28, 2025 | Khalil M | Not started | High Priority | November 12, 2024 7:11 PM | November 12, 2024 8:27 PM |  | Active Sprint
Security Audit and Compliance Documentation | Maintenance & Documentation | January 29, 2025 → January 30, 2025 | Khalil M | Not started | High Priority | November 12, 2024 7:12 PM | November 12, 2024 8:27 PM |  | Active Sprint
Initial Training Sessions for Non-Technical Staff | Maintenance & Documentation | January 31, 2025 → January 31, 2025 | Khalil M | Not started | High Priority | November 12, 2024 7:13 PM | November 12, 2024 8:27 PM |  | Active Sprint
Create Video Tutorials and Quick Reference Guides | Maintenance & Documentation | January 29, 2025 → January 30, 2025 | Khalil M | Not started | Medium Priority | November 12, 2024 7:13 PM | November 13, 2024 7:25 PM |  | Active Sprint
Follow-Up Training and Q&A Session | Maintenance & Documentation | January 31, 2025 | Khalil M | Not started | Medium Priority | November 12, 2024 7:14 PM | November 13, 2024 7:27 PM |  | Active Sprint
Ongoing Support Channel for CMS Assistance | Maintenance & Documentation | February 1, 2025 | Khalil M | Not started | Medium Priority | November 12, 2024 7:14 PM | November 13, 2024 7:43 PM |  | Active Sprint
Update and Review Maintenance Documentation | Maintenance & Documentation | February 1, 2025 | Khalil M | Not started | Medium Priority | November 12, 2024 7:15 PM | November 13, 2024 7:23 PM |  | Active Sprint